## Sheet1
Feature/Flow | Remark | Bug/Improvement/Query/Bug+Improvement | Remark
Dropdowns in create user form | They are browser default. Implement better looking component. | Improvement
Create User -> create password -> re enter password | values of create password and re enter password didn't match still the account was created. value of createpassword input was saved as the password. | Bug | already working
Log in -> accept new terms -> log out -> log in | accept new terms modal appears again. the case of a user completing kyc in multiple login sessions has to be handled. | Bug | working fine
GST Number input | implement check of gst format as the value is being input | Improvement
Input gst number -> Verify GST button clicked | browser alert displays prompting to enter business name. the ui should make it clear that both gst number and business name have to be filled before verification. also, replace alert with proper modal. | Bug
input business name -> verify gst button clicked | browser alert displays prompting to upload gst. the ui should make it clear that all of gst number, business name and gst file upload have to be filled before verification. also, replace alert with proper modal.
Entered gst number which is suspended - 07AAGFF2194N1Z1 | gst got verified. | Bug
Aadhaar number -> verify aadhar | same as gst verification | Bug
Upload aadhaar images -> verify aadhar button clicked | error - Cashfree could not read this aadhaar image in an alert. replace alert and have a custom message. | Bug
Upload aadhaar back (dummy image uploaded) -> verify aadhar button | aadhaar got verified. how is the back image being used for aadhaar verification? | Query
Entered pan details for a business account for kyc of individual - AAJFB9072E | pan got verified | Bug
Basic info and signing - entered dummy business name | kyc proceeded. the business name should match the entity name returned in gst verification payload | Bug
Bill -> accept contract | KYC submission failed error in alert | Bug
CSB V Rampup | Skipped after kyc submission failed. activation pending page. go to dashboard click redirected to Bill tab. the contract didn't have signature uploaded. after accepting terms and contidion contract, caught in the same loop - kyc failed, etc | Bug
Bill tab | rename to Terms and Condition | Improvement
Sign out | 419 - page expired error | Bug
Create use -> se;ect business type | on hover a cursor with disabled icon is displayed | Bug
/kyc-draft api is being hit with every change in put | this is wrong. kyc progress should be saved after a considerable number of fields are filled. best would be upon verification of each kyc type. | Bug | already working
KYC -> upload aadhaar front | uploaded file named "WhatsApp Image 2026-08-15 at 18.36.56.jpeg" got error file name is invalid. handle file names properly | Bug
At time of account creation entered name Akshat Tripathi but uploaded aadhaar of a different person | aadhaar got verified. this is wrong. | Bug | need to otp
Pan verification -> entered individual's pan instead of a business pan | pan got verified. this is wrong. | Bug
CSB V -> Billing Address | must be prefilled as per gst response. | Bug
Forgot Password | Internal Server error route not found exception | Bug | fix